## Sheet1
Project : PCA Communication – Test Cases |  | Project : PCA Communication – Test Cases |  |  | STATUS | SEVERITY
TEST CASES REPORT |  |  |  |  | Fixed | Critical
Id | TESTER | Test Case | Status | Comments | Open | Major
[5 empty] | Minor Issues | Minor
1 | santosh | Server Ip address and port number details are provided into conf.xml file. If any of these values are wrong, Connection was refused after few seconds | Cleared |  | Postponed | Suggestions
2 | santosh | Log file path also provided into conf.xml file. If it is not provided, the logfile path created at relative path | Cleared
3 | santosh | When you open your application, you will see UI part of all components | Cleared
4
4 | santosh | If the user clicked on “window close” button, it will shows a dialog box that you really want to close the UI. If yes, it closes the window. if Cancel, it will continues | Cleared
5 | santosh | At start up,only CONNECT button was enabled, so user able to understand connect his device. | Cleared
6 | santosh | When User pressed on CONNECT button, you are able to Select PCA device from a PCA list displayed by a InputDialogBox | Cleared
7 | santosh | Dialog box display two buttons Ok and Cancel. If you click Cancel, the UI window will get closed. If you clicked on Ok button without selecting PCA from list, the same dialog box displayed continuously until you selected a PCA. | Cleared
8 | santosh | Checkbox labels updated based on the selection. | Cleared
9 | santosh | Once you selected your PCA, and then clicked on Ok, you are now connected to respected PCA, the same status can be shown at left-bottom label and CONNECT button state change to DISCONNECT. Connection status is visible to you, until you clicked on DISCONNECT state of button. | Cleared
10 | santosh | When your PCA get connected, TCP socket connection started and receiving thread started to receive response from other side. | Cleared
11 | santosh | When your PCA get connected, you will able to select destination PCAs (one or more) displayed as checkboxes. “Select All” checkbox toggled for select all PCAs and deselect all PCAs. Once you select all PCAs by SelectAll checkbox, then if you want to deselect any checkbox, all checkboxes get deselected and you have to select again as your wish. | Cleared
12 | santosh | Until you select atleast one PCA checkbox, Message components such as Message ID textfield, and Message combobox will be in disable state. | Cleared
13 | santosh | After selecting PCA(s), all checkboxes disabled,MessageID Textfield and Message combobox get enabled and allow you to select MessageId and Message. | Cleared
14 | santosh | All messages stored in a text file named as Message.txt and populated to the combobox when application starts. User shall edit the text file to add/remove/modify the messages. | Cleared
15 | santosh | User was able to type a number in MessageID Textfield corresponding to the message of his choice when you pressed enter the same selected in the combo box next to it. | Cleared
16 | santosh | If the entered number is not existed in your text file, it displays an alert box and clears both Message components to default state when we click OK button. And you now able to reselect your message. | Cleared
17 | santosh | User was able to select a message from combobox of his choice,then the corresponding message id displayed in textfield. | Cleared
18 | santosh | The SEND button disabled until you selected a message. After you selected a message SEND button enabled and you are able to send message to selected PCAs | Cleared
19 | santosh | SEND button toggled as send and cancel button. Starting state is Send and changes to CANCEL as soon send is started. Soon after send is completed, changes back to SEND. If SEND is pressed, it initiates sending packet over tcp socket. | Cleared
20 | santosh | When sending initiated, Message Id Textfield and combobox get disabled (Checkboxes already disabled). So that you can avoid the changing of message and changing of destinations while data is sending and receiving ACKs. | Cleared
21 | santosh | After SEND button clicked, Message Panel-1 displays all messages outgoing from the connected PCA. These messages displayed in required format (Mean to say,includes direction indicator, destination, timestamp , msg id and initial part of message). | Cleared
22 | santosh | Message Panel 2 displays all incoming ACK messages to the connected PCA. Displayed messages includes direction indicator, source, timestamp , msg id and initial part of message. | Cleared
23 | santosh | Label right-bottom displays waiting status for ACK messages until it gets all ACK messages from all selected PCA destinations, to which Source PCA sent message. | Cleared
24 | santosh | Both message panels were synchronized with each other for scroll and other operations. | Cleared
25 | santosh | Clear button disabled until sending and receiving messages displayed into message panels in one send. | Cleared
26 | santosh | Clear button clears both panels. (Just you get feeling of clear screen as in DOS cmd screen or UNIX). | Cleared
27 | santosh | Once receiving all ACK messages get displayed, checkboxes automatically enabled. So that again you can able to send messages. | Cleared
28 | santosh | When you pressed DISCONNECT button, if there is no pending messages to send or receive, then TCP socket connection terminated and DISCONNECT changes to CONNECT state.And clear both message panes. After connect, button changes to disconnect and vice versa. | Cleared
29 | santosh | New separate Log text file created for each connection | Cleared
30 | santosh | Each Log text file had connection timestamp as part of filename. | Cleared
31 | santosh | All incoming and outgoing messages logged to log text file in windows not in linux | Cleared
32 | santosh | we should have 3 bytes of message Id .But if we assign more than 3 or less than 3 bytes to ID .it wl takes and send message to device | Cleared
33 | santosh | If we send message ID with more than 3 digits. Responce Acknolegment message will come back with 3 digit ID only | Cleared
34 | santosh | we want to make GUI look the same on screen resolutions in different operating systems | Cleared